## Project Planner
Project Plan for Payment Gateway
|  |  | 1 |  |  | Plan Duration
ACTIVITY | PLAN START | PLAN DURATION | PERIODS
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Preparation | 1 | 10 | bar: PERIODS 1 to PERIODS 10
Specifications | 1 | 15
Architecture | 2 | 20
Planning | 4 | 15
Detail Design | 4 | 20
Development | 4 | 35
Test Plan | 5 | 10
Testing and QA | 5 | 8
Documentation | 5 | 5